TPA.

AI Readiness Assessment

Findings and Recommendations

Sample Output

| Prepared by | Turnpoint Advisory |
| --- | --- |
| Prepared for | Meridian Recruitment Group |
| Assessment date | June 2026 |
| Classification | Sample ¦ Confidential |

Executive Summary   Sample

The assessment covers five dimensions of AI readiness across Meridian's business. Process and commercial readiness are the strongest signals. The business has the volume, the rate card, and the task structure to generate material returns quickly. Governance is the most immediate risk, not a future consideration. Four of the five opportunities identified are directly quantifiable. The fifth, client engagement monitoring, represents revenue protection and is treated separately.

Opportunities 01 and 02 are the starting point. Both deploy within 30 days without JobAdder integration and together recover more than $220,000 in annualised consultant time. They also establish the prompt frameworks, output standards, and review protocol that every subsequent opportunity depends on.

Opportunity 04 follows in Phase 2. Eighteen consultants are producing client-facing communications to no shared standard. The quality variance is unmanaged and visible to clients. Voice profiles close that gap at scale.

Opportunity 03 is an AI-powered early warning system for at-risk placements, representing $204,000 in annual revenue protection. It requires JobAdder API access and data structuring work before deployment, and is treated as a Phase 3 priority. It is not included in the $375,000 directional total.

Full arithmetic for each opportunity is in Section 3. All estimates are built from Meridian's own operating parameters.

| Opportunity | Est. Annual Value |
| --- | --- |
| 01 Proposal Generation | $36,720 |
| 02 Assessment Writeups | $183,600 |
| 03 Engagement Monitoring | Revenue protection (see Section 3) |
| 04 Consultant Voice Profiles | $137,700 |
| 05 Market Mapping | $19,584 |

Total directional upside (Opportunities 01, 02, 04 and 05)     ~$375,000 per annum

Five opportunities. $375,000 in directional annual upside across the four near-term opportunities. The sequencing and delivery plan are in this document.

Assessment Dimensions   Sample

Five dimensions assessed. Rated across four maturity levels: At Risk, Developing, Established, Scale-Ready.

| Dimension | Rating | Finding |
| --- | --- | --- |
| Process Readiness | Developing | 50-plus consultant-hours per week on manual writeups and proposals. Addressable within 30 days. |
| Data Readiness | Developing | JobAdder data present but inconsistently structured. Limits the more complex AI applications. |
| Workforce Readiness | Developing | Ad hoc individual AI use without governance. Efficiency gains are partial and inconsistent. |
| Governance Readiness | At Risk | No usage policy, no output review standard, no accountability structure. An active liability. |
| Commercial Readiness | Established | Volume, rate card, and task structure all support rapid payback. Sequencing is the only constraint. |

Process Readiness

Nine proposals and 90 writeups per week. At 90 and 45 minutes respectively, those two tasks consume more than 50 consultant-hours weekly on structurally repetitive work. AI-assisted drafting addresses both within 30 days. No custom build required. No CRM integration in the initial phase.

Data Readiness

JobAdder holds the data Meridian needs. The constraint is consistency: field completion rates are variable, naming conventions differ, and stage definitions are not applied uniformly. Opportunities 01, 02, and 04 are unaffected. They do not require JobAdder integration initially. Opportunity 03 does. Data structuring is scoped in Phase 3.

Workforce Readiness

Consultants are already using AI individually. Use is ad hoc and ungoverned. The business is capturing a fraction of the available efficiency and none of the consistency benefit. The intervention required is operational: a governed team-wide workflow with defined prompt frameworks and a mandatory review step before any AI-generated output reaches a client.

Governance Readiness

No AI usage policy. No output review standard. Client-facing content generated by AI is leaving the business on individual consultant judgement. This is the most immediate risk. A one-page policy, a defined review step, and a clear accountability structure can be operational within 30 days. This work begins in Phase 1, not after deployment.

Commercial Readiness

The commercial case is not marginal. The volume is there, the rate card is there, and the task structure makes the return fast. Deploy without governance and you create liability. Deploy without data structure and you limit the highest-value opportunity. The 90-day plan avoids both.

Consultants are already using AI. The business is not governing it. That is the only thing standing between Meridian and Phase 1.

Opportunity Register   Sample

Five opportunities, prioritised by commercial impact. Summary below. Full detail follows.

|  | Description | Est. Annual Value |
| --- | --- | --- |
| 01 Proposals | AI drafting: 90 min to 30 min per proposal | $36,720 |
| 02 Assessment Writeups | AI writeups: 45 min to 15 min per candidate summary | $183,600 |
| 03 Engagement Monitoring | Early warning system for at-risk placements | See Section 3 |
| 04 Voice Profiles | Consistent brand-aligned communications across 18 consultants | $137,700 |
| 05 Market Mapping | 60% reduction in senior consultant BD research time | $19,584 |

Total directional upside     ~$375,000 built from Meridian's operating data

Value estimates are directional and built from Meridian's operating parameters. Full arithmetic below.

Opportunity 01

AI-Assisted Proposal Generation

AI drafting cuts proposal time from 90 minutes to 30 minutes

Dimensions: Process Readiness Complexity: Low

Current state

Consultants write client proposals manually. Each takes approximately 90 minutes. At 0.5 proposals per consultant per week, the team produces 9 per week. Proposals follow a consistent structure: role summary, client context, key requirements, commercial terms. The structural consistency of the format is precisely what makes AI-assisted drafting effective here. Time savings begin from day one of deployment.

Proposed application

Consultant inputs role, client context, and key requirements into a structured brief. The system generates a complete draft. Consultant reviews, refines where needed, and sends. Target time: 30 minutes per proposal. No JobAdder integration required in initial deployment. Prompt framework is built once and used by the full team. Operational within 30 days.

Value calculation 9 proposals per week 60 minutes saved per proposal $85/hr fully loaded consultant rate 48 working weeks = 9 x 1.0 hr x $85 x 48 = $36,720 per annum (directional) Note: 0.5 proposals per consultant per week is a conservative floor. Teams running active BD programs typically exceed this.

Opportunity 02

Automated Candidate Assessment Writeups

AI generation cuts writeup time from 45 minutes to 15 minutes per candidate

Dimensions: Process Readiness Complexity: Low

Current state

Consultants write candidate assessment summaries manually after each interview. Average time: 45 minutes per writeup. At 5 writeups per consultant per week across 18 consultants, the team produces 90 per week. This is the highest-volume, highest-frequency manual task in the business. Unlike proposals, it recurs on every placement for every consultant. The compounding effect on total consultant hours is significant.

Proposed application

Consultant provides interview notes or completes a structured input form. The system generates the full writeup. Consultant reviews and approves before the document is used. Target: 15 minutes per writeup. No JobAdder integration required. Prompt framework built once, used by the full team from day one. Operational within 30 days. This is Priority 1: highest volume, fastest to deploy, largest annualised return.

Value calculation 18 consultants x 5 writeups per week = 90 per week 30 minutes saved per writeup $85/hr fully loaded consultant rate 48 working weeks = 90 x 0.5 hr x $85 x 48 = $183,600 per annum (directional) Note: 5 writeups per consultant per week represents a mid-range estimate for a consultant carrying 3 to 4 active roles.

Opportunity 03

AI-Powered Client Engagement Monitoring

Early warning system surfaces at-risk placements before revenue is lost

Dimensions: Data Readiness, Commercial Readiness Complexity: High

Current state

Client engagement is managed manually across the team. No early warning system exists for placements at risk of delay or withdrawal. Consultants rely on experience and relationship instinct to identify deteriorating client situations. By the time a withdrawal is confirmed, the revenue is already gone. There is no mechanism to intervene before the commercial event occurs.

Proposed application

An AI monitoring layer applied over JobAdder data. The system identifies patterns historically associated with client disengagement: response time deterioration, stage stalling, drop-off in communication frequency. It surfaces at-risk placements to the responsible consultant before the revenue event, creating an intervention window that does not currently exist. Requires JobAdder API access and a data structuring sprint prior to deployment. Phase 3 priority.

Value calculation Conservative assumption: 2 placements per month protected from withdrawal or delay $8,500 average placement fee = 2 x $8,500 x 12 months = $204,000 revenue protected per annum This opportunity represents revenue protection, not cost reduction. It is excluded from the $375,000 directional upside total.

Opportunity 04

Consultant Voice Profiles and Brand-Consistent Communications

AI voice profiles deliver consistent, brand-aligned client communications at scale

Dimensions: Workforce Readiness, Process Readiness Complexity: Medium

Current state

Eighteen consultants produce client-facing communications to no shared standard. Tone, structure, and brand alignment vary significantly by individual. The quality gap is visible to clients and currently unmanaged. Clients working with different consultants receive materially different communication experiences. There is no scalable mechanism to address this without adding overhead.

Proposed application

AI-generated voice profiles per consultant, trained on a library of approved client communications. The system outputs emails, follow-up notes, and role summaries that are brand-consistent and individually calibrated to each consultant's style. Consultant reviews before sending. Requires a communication sample library and per-consultant prompt calibration. Phase 2 deployment, after the team has operational experience with AI-assisted drafting from Opportunities 01 and 02.

Value calculation 18 consultants 1.5 client communications per day 15 minutes saved per communication $85/hr fully loaded consultant rate 240 working days = 18 x 1.5 x 0.25 hr x $85 x 240 = $137,700 per annum (directional) Note: 1.5 comms per consultant per day is a conservative floor. Adjust for actual team volume to refine this estimate.

Opportunity 05

AI-Assisted Market Mapping and Target List Generation

Auto-refreshed BD target lists cut senior consultant research time by 60%

Dimensions: Process Readiness, Commercial Readiness Complexity: Medium

Current state

BD target lists are built manually by senior consultants, consuming approximately four hours per week per person. Lists go stale quickly between builds. No systematic refresh process exists. Senior consultant time is being spent on a research task that does not require it.

Proposed application

AI-assisted market mapping across LinkedIn, company databases, and sector signals. Auto-generates and refreshes target lists by sector, geography, and hiring signal. Estimated 60% reduction in senior consultant BD research time. Low implementation complexity. No dependency on governance or data structure work. Runs as a background task alongside Phase 1 from day one.

Value calculation 2 senior consultants x 4 hours per week on BD research 60% time reduction $85/hr fully loaded consultant rate 48 working weeks = 2 x 4 x 0.6 x $85 x 48 = $19,584 per annum (directional) Note: 60% reduction is consistent with AI-assisted research tools in comparable BD functions. Conservative floor is 40%.

Opportunities 01 and 02 alone recover $220,000 in annualised consultant time. Opportunities 04 and 05 add a further $157,000. Opportunity 03 represents additional revenue protection scoped separately.

90-Day Action Plan   Sample

Three phases. Defined objectives, specific actions, clear handoffs. Structured to be briefed to an internal team or handed to an implementation partner without further scoping.

| Phase | Timing | Objective | Opportunities |
| --- | --- | --- | --- |
| Phase 1 | Days 1 to 30 | Deploy Opportunities 01 and 02. Establish governance baseline. | 01, 02, 05 (background) |
| Phase 2 | Days 31 to 60 | Deploy Opportunity 04. Build consistent output standards. | 04 |
| Phase 3 | Days 61 to 90 | Scope Opportunity 03. Commission next phase if proceeding. | 03 |

Phase 1  Days 1 to 30

Deploy Opportunities 01 and 02. Establish governance baseline.

- Select AI tool and build prompt templates for assessment writeups and proposal generation. Run a two-consultant pilot, measure time against baseline, then expand to the full team.

- Implement the review step from day one: consultant checks AI output before it reaches a client. Draft and circulate the AI usage policy.

- Opportunity 05 starts as a background task: one senior consultant, 30 minutes per week, building and refreshing BD target lists.

Phase 2  Days 31 to 60

Deploy Opportunity 04. Build consistent output standards.

- Compile the communication library: 5 to 10 approved client communications per consultant as calibration examples. Build AI voice profiles per consultant and calibrate against Meridian's brand standards.

- Roll out under the Phase 1 review protocol. No AI-generated communication reaches a client without consultant sign-off.

- Quality review at day 45. Spot-check outputs against the library benchmark. Finalise and circulate the AI usage policy based on Phase 1 experience.

Phase 3  Days 61 to 90

Scope Opportunity 03. Commission next phase if proceeding.

- Engage JobAdder on API access. Conduct a data audit: field completion rates, naming consistency, and stage definition alignment across the team.

- Map the data structure required for the AI engagement monitoring system. Identify gaps and remediation effort.

- Commission next phase based on scope. Review Phase 1 and 2 outcomes and use confirmed time savings to sharpen the Opportunity 03 value case.

Ninety days from a decision to a governed, team-wide AI workflow across three of the five opportunities, with the fourth scoped and ready to commission.

Working with Turnpoint Advisory   Sample

Turnpoint Advisory works with privately owned and founder-led SMEs navigating the complexity that comes with growth. Our principals have led operations, finance, and transformation programs inside businesses like Meridian. Not as external observers. As the people accountable for the outcomes. That is the difference between advice and execution.

Three paths forward.

| Option | Description |
| --- | --- |
| Transformation Support Fee scoped to engagement | Structured delivery coordination across the agreed opportunities and phases. Turnpoint maintains program momentum, manages delivery sequencing, tracks initiative ownership, and provides governance oversight and reporting. For a program of this scope, this is the path that captures the full upside. |
| Implementation Blueprint | Converts the 90-day action plan into a workstream-level delivery plan: initiative ownership, governance framework, sequencing, risk and dependency mapping, and an executive readout. Defines the scope and pace of any subsequent Transformation Support engagement. |
| Use this document as your brief | Section 4 contains enough structure to engage a technology partner or internal team on Opportunities 01 and 02 directly. No further scoping required. |

Ready to move? Contact Tony Sivaa to discuss which path makes sense for Meridian. The conversation starts with which opportunities to move on first and what level of support is right. Tony Sivaa ¦ Turnpoint Advisory ¦ turnpointadvisory.com.au

Most businesses at this scale have identified what needs to change. The gap is execution capacity. That is what Turnpoint provides.

This document is a directional assessment prepared from information provided by and discussions with Meridian Recruitment Group. Value estimates are built from stated operating parameters and are directional in nature. They are not guaranteed commercial outcomes. Actual results will depend on implementation quality, team adoption, and operating conditions at the time of deployment.